## Slide 1: Development
September 2025

## Slide 2: TransANT UNO Multi 40ft

## Slide 3: Current status - TransANT UNO Multi 40ft
Drawing set in status “Freigabe DVM”  ready for approval by DVM
Calculation (static + dynamic) completed
Calculation report completed
waiting for approval by DVM to finish drawing release process

## Slide 4
transport goods
TransANT UNO tank 88m³

## Slide 5: Current status - TransANT UNO tank 88m³
3D model and 2D drawings finished
3D model and 2D drawings submitted to Poltavvagon
Calculation finished (static + dynamic)
waiting for feedback from Poltavvagon to start drawing release process

## Slide 6: Next steps - TransANT UNO Multi 40ft
Approval of drawing set
Approval of strength report (TransANT)

## Slide 7: Next steps - TransANT UNO tank 88m³
Releasing of 3D model and 2D drawings
Finalization of calculation report

## Slide 8: Next steps - generally
Reworking of the drawing set for the 70ft TimberTop for RCA
 finished End of September
Reworking of the drawings of the hole portfolio in regard of surface treatment
 finished End of September

## Slide 9: Next steps - projects
development of the shortest possible open top wagon
 most versatile wagon for transporting very heavy goods
 target 1.5t lighter than 33ft DB MultiTop
Possible finish date of drawing set  End of 2025